## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
Not too sure what/where to unit test currently | 13 | 3 | 39 | 2023-03-20 | Resolved | R | Updated task diagram and found good locations for unit tests
Testing physics task initially without a display | 20 | 5 | 100 | 2023-03-20 | Mitigated | M | Set up satchels first in phys/monitor to watch how they drop
0
0
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100