## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
When try to stop physics test on game over, game can freeze up | 20 | 20 | 400 | 2023-04-12 | Mitigated | M | Physics task continues to run after game is over but gets reset to a default state when game is reactivated
Testing physics task initially without a display | 20 | 5 | 100 | 2023-03-20 | Mitigated | M | Set up satchels first in phys/monitor to watch how they drop
Some inconsistancy between display/phys for satchel hit | 5 | 8 | 40 | 2023-04-12 | Mitigated | O | Physics task checks for a hit slightly above the ground instead of when ground is hit
Not too sure what/where to unit test currently | 13 | 3 | 39 | 2023-03-20 | Resolved | R | Updated task diagram and found good locations for unit tests
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100